## Liquidation Road Map
Liquidation Road Map
№ | Task | Checkbox | Status | Total tasks | Open | Completed
1 | General review and discussion of the liquidation strategy with the Client | FALSE | Not started | 32 | 31 | 1
| send balances to the Client with a request as to what to do with them | TRUE | Completed
| to approve the liquidator | FALSE | In progress | Progress (%)
| license revocation (if need) | FALSE | Not started | 3.125%
| cancellation of license (if need) | FALSE | Not started
2 | Preparation of documents on the establishment of a liquidation commission | FALSE | Not started
3 | Registration of inventory results | FALSE | Not started
4 | Debtor/creditor notification and debt collection | FALSE | Not started
| notify to counter-agents for the liquidation of the enterprise | FALSE | Not started
| request all acts of reconciliation with counterparties for all contracts | FALSE | Not started
| closing of contracts with counterparties | FALSE | Not started
5 | Preparation of documents for closing a bank account (except for the main one) | FALSE | Not started
6 | Dismissal of employees and preparation of relevant documentation in accordance with labor legislation, informing the relevant labor authorities | FALSE | Not started
| tax and salary reconciliation | FALSE | Not started
| dismissal by agreement of the parties | FALSE | Not started
| payment for unused holidays | FALSE | Not started
| sign all documents that the director must sign | FALSE | Not started
| preparation of dismissal documents | FALSE | Not started
| preparation of a decision such as dismissing a director and appointing a liquidator in one decision | FALSE | Not started
7 | Preparation of documents for the keys to the liquidator | FALSE | Not started
| registration of Medok keys for the liquidator | FALSE | Not started
| registration of Bank keys for the liquidator | FALSE | Not started
8 | Liquidation by a VAT payer (without budgetary reimbursement, budgetary reimbursement is discussed separately) | FALSE | Not started
| budgetary reimbursement | FALSE | Not started
| Liquidation by a VAT payer | FALSE | Not started
9 | Support during a tax inspection | FALSE | Not started
10 | Support during the inspection of the Pension Fund of Ukraine on the payment of the unified social contribution | FALSE | Not started
| contact PFU regarding liquidation | FALSE | Not started
11 | Preparation and submission of interim and liquidation reports (balance sheet and profit) | FALSE | Not started
12 | Preparation of documentation for transfer to the archive of documents subject to mandatory storage | FALSE | Not started
| reconciliation of archives for the availability of all documents for all years | FALSE | Not started
13 | Preparation of documentation on the destruction of seals/stamps | FALSE | Not started
TOTAL |  | FALSE